## Project
Total Project Tracking |  |  | Note: - Done: Your feature has been finished - To do: Your feature will be developed - Doing: Your feature is being developed
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | My Registrations | Customer | Customer | Show the list of user's registrations + the sider with the subject search box, subject categories, static contacts/links - Each registration includes below information: id, subject, registration time, package, total cost, status, valid from, valid to; - If the registration is still in the submitted status, the users can choose to cancel it or comming back to the Subject Register pop-up to edit it) | HoanTX | Done | Done | Done
2 | Practices List | Customer | Customer | This page allows the user to view the list of quiz practices that s/he has taken | HoanTX | Done | Done | Done
3 | Reset Password | Common | Customer, Admin, Expert, Sale, Maketer | The user to input his/her email to receive the reset password link. This link is sent to the user's email for his/her password resetting. - On clicking the link, the user is redirected to the password resetting page in which s/he input new password (twice) for the system access - Note that the link is only available for a specific time duration as configured in the system config file. | HoanTX | Done | Done | Done
4 | Sliders List | Marketing | Maketer | Show the paginated list of sliders (including sliders' id, title, image, backlink, status) - The user can filter the sliders by the status + search by title or backlink - For each slider, the user can choose to hide, show, edit it | HoanTX | Done | Done | Done
5 | Slider Details | Marketing | Maketer | Show detailed slider information (image, title, backlink, status, notes) | HoanTX | Done | Done | Done
6 | Subjects List | Public | Customer | Show the subjects paginatedly (sorted by updated date, paginated) + the sider with the subject search box, subject categories, featured subjects, and static contacts/links; - Shown subject information includes its thumbnail, title, tag line, lowest price package option (list price, sale price); - The user is redirected to the subject's details on his/her clicking on the subject - The user can choose to register to the subject by clicking the Register button | HoanTX | Done | Done | Done
7 | Subjects Register | Public | Customer | This is a pop-up screen which allow the user to register for access a subject. On this screen, the user needs to choose appropriate subject price package & input his/her information (full name, email, mobile, gender); A logged in user doesn't have to input those contact information | HoanTX | Doing | Doing | Doing
| User Register | Common | Customer, Admin, Expert, Sale, Maketer | This is a pop-up screen which allows the user to register himself/herself to the system by inputing following information: full name, gender, email, mobile; User then need to verify by clicking the link sent via email to him/her before being able to access the system | HuongNI | Done | Done | Done
9 | Home | Public | Customer | Show sliders, hot posts, featured subjects + the sider with the latest posts, static contacts/links - Shown slider information includes its image and title; the user is redirected to the slider's backlink on his/her clicking - Shown post information includes its thumbnail, title, post date; the user is redirected to the post's details on his/her clicking - Shown subject information includes its thumbnail, title, tag line; the user is redirected to the subjectt's details on his/her clicking | HuongNI | Done | Done | Done
10 | Blogs List | Public | Customer | Show the posts paginatedly (sorted by updated date) + the sider with the post search box, posts categories, latest posts, static contacts/links; Shown post information includes its thumbnail, title, category, brief-info; the user is redirected to the post's details on his/her clicking | HuongNI | Done | Done | Done
11 | Blog Details | Public | Customer | Show post details (including title, author, updated date, category, and post details) + the sider with the post search box, posts categories, latest posts, static contacts/links | HuongNI | Done | Done | Done
12 | Post Details | Marketing | Marketer | Show detailed post information (thumbnail, category, title, brief information, description, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them | HuongNI | Done | Done | Done
13 | Dashboard | Marketing | Marketer | Show statistics of new subjects (new, all), new registrations (success, cancelled, submitted), revenues (total, by subject categories), customers (newly registered, newly bought), and the trend of order counts (success, all) by day for the last 7 days (the start date & end date can be adjustable) | HuongNI | Done | Done | Done
14 | Simulation Exam | Customer | Customer | This page allows the user to view the existing exams of the subject that s/he has the access. • List columns: id, subject, simulation exam, level, #question, duration, and pass rate • The user can filter the list by the subject + search list items by the exam name From the list, the user can choose to take the exam to see the exam details, and then to go to Quiz Handle page to practice that relevant simulation exam. | HuongNI | Done | Done | Done
15 | User Login | Common | Customer, Admin, Expert, Sale, Maketer | The User to input email and password to login | TuanKD | Done | Done | Done
16 | Subjects List | Course Content | Admin, Expert | Show the list of course paginatedly. The admin can see all list of course while the expert can only see his course | TuanKD | Done | Done | Done
17 | Subject Lesson | Course Content | Admin, Expert | The page shows the list of lesson for a selected package. | TuanKD | Done | Done | Done
18 | Subject Dimension | Course Content | Admin, Expert | The page allows the admin/expert to input or edit subject dimension information | TuanKD | Done | Done | Done
19 | Price Package | Course Content | Admin, Expert | The page allows the admin to input or edit price of course. The expert can only view the information | TuanKD | Done | Done | Done
20 | Lesson Details | Course Content | Admin, Expert | The page allows the admin/expert to input or edit the lesson information | TuanKD | Done | Done | Done
21 | New Subject | Course Content | Admin | This screen allows the Admin to create a new subject in the system. Only Admin users have access to this function. | TuanKD | Done | Done | Done
22 | Subject Details | Course Content | Admin, Expert | This page allows the admin and the assigned expert to access and prepare the subject information, including the course general information, the dimension, and price package. | TuanKD | Done | Done | Done
23 | Edit Profile | Common | Customer, Admin, Expert, Sale, Maketer | Screen that allows users to edit personal information | ThuanHD | Done | Done | Done
24 | Quizzes List | Course Content | Admin, Expert | The screen allows the expert to manage the quizzes including viewing the list of ID Title, Subject, Description, Level, Number of Questions, Duration (minutes), Pass Rate (%), Quiz Type | ThuanHD | Done | Done | Done
25 | Quiz Details | Course Content | Admin, Expert | The screen provides information fields of an untaken test for experts to edit and add information including Title, Subject, Exam Level, Duration (minutes), Pass Rate (%), Quiz Type, Description, Total number of questions, Question allocation | ThuanHD | Done | Done | Done
26 | Registrations List | Sale | Saler | The screen allows the seller to search and filter the list of courses that the user has registered for. | ThuanHD | Done | Done | Done
27
28
29
30
31

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | Notes
1 | My Registrations | Customer | Show the list of user's registrations + the sider with the subject search box, subject categories, static contacts/links - Each registration includes below information: id, subject, registration time, package, total cost, status, valid from, valid to; - If the registration is still in the submitted status, the users can choose to cancel it or comming back to the Subject Register pop-up to edit it) | HoanTX | Done | Done |  | 60
2 | Practices List | Customer | This page allows the user to view the list of quiz practices that s/he has taken | HoanTX | Done | Done |  | 60
3 | User Login | Common | The User to input email and password to login | TuanKD | Done | Done |  | 60
4 | Subjects List | Course Content | Show the list of course paginatedly. The admin can see all list of course while the expert can only see his course | TuanKD | Done | Done |  | 60
5 | User Register | Common | This is a pop-up screen which allows the user to register himself/herself to the system by inputing following information: full name, gender, email, mobile; User then need to verify by clicking the link sent via email to him/her before being able to access the system | HuongNI | Done | Done |  | 60
6 | Home | Public | Show sliders, hot posts, featured subjects + the sider with the latest posts, static contacts/links - Shown slider information includes its image and title; the user is redirected to the slider's backlink on his/her clicking - Shown post information includes its thumbnail, title, post date; the user is redirected to the post's details on his/her clicking - Shown subject information includes its thumbnail, title, tag line; the user is redirected to the subjectt's details on his/her clicking | HuongNI | Done | Done |  | 120
7 | Edit Profile | Common | Screen that allows users to edit personal information | ThuanHD | Done | Done |  | 60
8 | Quizzes List | Course Content | The screen allows the expert to manage the quizzes including viewing the list of ID Title, Subject, Description, Level, Number of Questions, Duration (minutes), Pass Rate (%), Quiz Type | ThuanHD | Done | Done |  | 60
60
60
60
240
960

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | Notes
1 | Reset Password | Common | The user to input his/her email to receive the reset password link. This link is sent to the user's email for his/her password resetting. - On clicking the link, the user is redirected to the password resetting page in which s/he input new password (twice) for the system access - Note that the link is only available for a specific time duration as configured in the system config file. | HoanTX | Done | Done |  | 120
2 | Sliders List | Marketing | Show the paginated list of sliders (including sliders' id, title, image, backlink, status) - The user can filter the sliders by the status + search by title or backlink - For each slider, the user can choose to hide, show, edit it | HoanTX | Done | Done |  | 60
3 | Slider Details | Marketing | Show detailed slider information (image, title, backlink, status, notes) | HoanTX | Done | Done |  | 60
4 | Subject Lesson | Course Content | The page shows the list of lesson for a selected package. | TuanKD | Done | Done |  | 120
5 | Subject Dimension | Course Content | The page allows the admin/expert to input or edit subject dimension information | TuanKD | Done | Done |  | 60
6 | Price Package | Course Content | The page allows the admin to input or edit price of course. The expert can only view the information | TuanKD | Done | Done |  | 60
7 | My Courses | Customer | for the customer to view his/her access-allowed courses | Hoan | Doing | Pending
8 | Blogs List | Public | Show the posts paginatedly (sorted by updated date) + the sider with the post search box, posts categories, latest posts, static contacts/links; Shown post information includes its thumbnail, title, category, brief-info; the user is redirected to the post's details on his/her clicking | HuongNI | Done | Done |  | 60
9 | Blog Details | Public | Show post details (including title, author, updated date, category, and post details) + the sider with the post search box, posts categories, latest posts, static contacts/links | HuongNI | Done | Done |  | 60
10 | Questions List | Test Content | The existing questions list for a specific subject/course are shown here (paginatedly). On this screen, the admin/expert is allowed to filter the questions by the subject, lesson, dimension(s), level, status + search the questions by content Below information are shown for each quesiton in the list: id, content, subject /dimension /lesson, level, status + options to show, hide, edit it; The page also allows the user to import the question (redirect him/her to the Questions Import pop-up screen. | Hoan | Doing | Pending
11 | Post Details | Marketing | Show detailed post information (thumbnail, category, title, brief information, description, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them | HuongNI | Done | Done |  | 120
12 | Question Import | Test Content | This is a pop-up screen which allows user to choose import file and then import the questions in the file into the questions bank. The screen also provides the option for the user to download the sample import template. | Hoan | Doing | Pending
13 | Quiz Details | Course Content | The screen provides information fields of an untaken test for experts to edit and add information including Title, Subject, Exam Level, Duration (minutes), Pass Rate (%), Quiz Type, Description, Total number of questions, Question allocation | ThuanHD | Done | Done |  | 120
14 | Registrations List | Sale | The screen allows the seller to search and filter the list of courses that the user has registered for. | ThuanHD | Done | Done |  | 120
15
16
17
18
19
20 | [8 empty] | 960
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | Notes
1 | Subjects List | Public | Show the subjects paginatedly (sorted by updated date, paginated) + the sider with the subject search box, subject categories, featured subjects, and static contacts/links; - Shown subject information includes its thumbnail, title, tag line, lowest price package option (list price, sale price); - The user is redirected to the subject's details on his/her clicking on the subject - The user can choose to register to the subject by clicking the Register button | HoanTX | Done | Done
2 | Lesson Details | Course Content | The page allows the admin/expert to input or edit the lesson information | TuanKD | Done | Done
3 | New Subject | Course Content | This screen allows the Admin to create a new subject in the system. Only Admin users have access to this function. | TuanKD | Done | Done
4 | Dashboard | Marketing | Show statistics of new subjects (new, all), new registrations (success, cancelled, submitted), revenues (total, by subject categories), customers (newly registered, newly bought), and the trend of order counts (success, all) by day for the last 7 days (the start date & end date can be adjustable) | HuongNI | Done | Done |  | 240
5 | Queston Details | Course Content | This page allows the admin/expert to input or edit questions information, including following information: subject, dimension(s), lesson, status, content, media (image, audio, video – with preview option), answer options (with the key marked + ability to add, edit, delete), and explanation | ThuanHD | Doing | To Do
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | Notes
1 | Subjects Register | Public | This is a pop-up screen which allow the user to register for access a subject. On this screen, the user needs to choose appropriate subject price package & input his/her information (full name, email, mobile, gender); A logged in user doesn't have to input those contact information | HoanTX | Doing | Doing
2 | Simulation Exam | Customer | This page allows the user to view the existing exams of the subject that s/he has the access. • List columns: id, subject, simulation exam, level, #question, duration, and pass rate • The user can filter the list by the subject + search list items by the exam name From the list, the user can choose to take the exam to see the exam details, and then to go to Quiz Handle page to practice that relevant simulation exam. | HuongNI | Done | Doing
3 | Subject Details | Course Content | This page allows the admin and the assigned expert to access and prepare the subject information, including the course general information, the dimension, and price package. | TuanKD | To Do | To Do |  | 120
4 | [7 empty] | 240
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40